## Gantt Chart
Project #3 - GANTT CHART
PROJECT TITLE |  | CIVE 202 PROJECT #3 |  |  |  |  | COMPANY NAME | [6 empty] | Group P3-G11
PROJECT MANAGER |  | Jessica Tackett |  |  |  |  | START DATE | [6 empty] | 2026-02-26
[7 empty] | END DATE | [6 empty] | 2026-03-31
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | WEEK 1 (2/23-2/27) |  |  |  |  | WEEK 2 (3/2-3/6) |  |  |  |  | WEEK 3 (3/9-3/20)
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Data Processing
1.1 | Create Gantt Chart | Jessica T | 2026-02-26 | 2026-02-26 | 0 | 100% | bar: WEEK 1 (2/23-2/27) R to WEEK 2 (3/2-3/6) M
1.1.1 | Read and Understand Client Prompt | Andrew C | 2026-02-26 | 2026-03-03 | 7 | 100% | bar: WEEK 1 (2/23-2/27) R to WEEK 2 (3/2-3/6) M
1.2 | Complete Additional Necessary Research | Kruvel W | 2026-02-26 | 2026-03-07 | 11 | 100% | bar: WEEK 1 (2/23-2/27) F to WEEK 2 (3/2-3/6) T
2 | Scope of Work
2.1 | Write Project Goals | Nathan J | 2026-02-26 | 2026-03-31 | 3 | 100% | bar: WEEK 1 (2/23-2/27) F to WEEK 2 (3/2-3/6) M
2.2 | Write Project Tasks | Jessica T | 2026-02-26 | 2026-03-31 | 3 | 100% | bar: WEEK 1 (2/23-2/27) F to WEEK 2 (3/2-3/6) M
2.3 | Write Project Deliverables | Andrew C | 2026-02-26 | 2026-03-31 | 3 | 100% | bar: WEEK 1 (2/23-2/27) F to WEEK 2 (3/2-3/6) M
2.4 | Finialize SOW | Kruvel W | 2026-02-26 | 2026-03-31 | 4 | 100% | bar: WEEK 2 (3/2-3/6) M to WEEK 2 (3/2-3/6) R
3 | Scenario Development
3.1 | Evaluate first scenario in automated Python Model | Nathan J | 2026-02-26 | 2026-03-07 | 11 | 100% | bar: WEEK 2 (3/2-3/6) M to WEEK 2 (3/2-3/6) W
3.2 | Evaluate second scenario in automated Python Model | Jessica T | 2026-02-26 | 2026-03-14 | 18 | 100% | bar: WEEK 2 (3/2-3/6) M to WEEK 2 (3/2-3/6) R
3.2.1 | Evaluate third scenario in automated Python Model | Andrew C | 2026-02-26 | 2026-03-24 | 28 | 100% | bar: WEEK 2 (3/2-3/6) M; WEEK 2 (3/2-3/6) W to WEEK 2 (3/2-3/6) F
4 | Python Code
4.1 | Project #3 - Week 7 lab | Kruvel W | 2026-02-26 | 2026-02-26 | 0 | 100% | bar: WEEK 1 (2/23-2/27) F to WEEK 2 (3/2-3/6) M
4.2 | Project #3 - Week 8 lab | Nathan J | 2026-02-26 | 2026-03-06 | 10 | 100% | bar: WEEK 2 (3/2-3/6) M; WEEK 2 (3/2-3/6) F
4.3 | Project #3 - Week 9 lab | Jessica T | 2026-02-26 | 2026-03-13 | 17 | 100% | bar: WEEK 2 (3/2-3/6) M; WEEK 3 (3/9-3/20) F
4.4 | Work on the final Project #3 Code | Andrew C | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M to WEEK 2 (3/2-3/6) R
4.4 | - Translate Excel logic into python | Kruvel W | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M to WEEK 2 (3/2-3/6) R
4.4 | - Implement sequential user inputs | Nathan J | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M to WEEK 2 (3/2-3/6) R
4.4 | - Generate a final mix design output | Jessica T | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M to WEEK 2 (3/2-3/6) R
5 | Results Validation
5.1 | Write Introduction/Background of Technical Report | Andrew C | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M to WEEK 2 (3/2-3/6) T
5.2 | Write Methods (Excel to Python traslation and parameters) of Technical Report | Kruvel W | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M; WEEK 2 (3/2-3/6) R to WEEK 3 (3/9-3/20) M
5.3 | Write Results/Discussion of Technical Report | Nathan J | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M; WEEK 2 (3/2-3/6) R to WEEK 3 (3/9-3/20) M
5.4 | Write Reference List of Technical Report | Jessica T | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M
6 | Annotated Code Document
6.1 | Review the finished Python Code | Andrew C | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M; WEEK 2 (3/2-3/6) R to WEEK 2 (3/2-3/6) F
6.2 | Assign parts of the code to annotate for each team member | Kruvel W | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M; WEEK 2 (3/2-3/6) F
6.3 | Complete the Annontated Code Document | Nathan J | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M; WEEK 2 (3/2-3/6) F to WEEK 3 (3/9-3/20) M
7 | Project 2 Reflection
7.1 | Put all documents and links into GitHub including the code, data, and a README file | Andrew C | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M; WEEK 3 (3/9-3/20) W to WEEK 3 (3/9-3/20) R
7.2 | Reflection Quiz | All | 2026-02-26 | 2026-03-31 | 35 | 100% | bar: WEEK 2 (3/2-3/6) M; WEEK 3 (3/9-3/20) F